## ManualDeliveryResults
No. ref | Task | Category | Expected Duration Seconds | Expected Duration | Start | 1 | Success | Comments | 2 | Success | Comments | 3 | Success | Comments | 4 | Success | Comments | 5 | Success | Comments | Average | Expected | Lead
1.01 | Communicate Start | Initialise Job | 0:05 | 300 | 0:00 | 83 | TRUE |  | 104 | TRUE |  | 38 | TRUE |  | 74 | TRUE |  | 33 | TRUE |  | 66.4 | 300 | 233.6
1.02 | Copy Files | Copy Files | 0:05 | 300 | 0:05 | 249 | TRUE |  | 218 | TRUE |  | 256 | FALSE | Folder incorrectly named | 192 | TRUE |  | 253 | TRUE |  | 233.6 | 300 | 66.4
1.03 | Back up Files | Prepare Infrastructure | 0:05 | 300 | 0:10 | 177 | TRUE |  | 189 | TRUE |  | 104 | TRUE |  | 177 | TRUE |  | 206 | TRUE |  | 170.6 | 300 | 129.4
1.04 | Shut Down Services | Prepare Infrastructure | 0:10 | 600 | 0:15 | 203 | TRUE |  | 181 | TRUE |  | 79 | TRUE |  | 145 | TRUE |  | 176 | TRUE |  | 156.8 | 600 | 443.2
1.05 | Backup of Database | Apply Modfications | 0:05 | 300 | 0:25 | 59 | TRUE |  | 106 | TRUE |  | 76 | TRUE |  | 90 | TRUE |  | 60 | TRUE |  | 78.2 | 300 | 221.8
1.06 | Copy Files | Apply Modfications | 0:05 | 300 | 0:30 | 293 | TRUE |  | 246 | TRUE |  | 181 | TRUE |  | 323 | TRUE |  | 156 | TRUE |  | 239.8 | 300 | 60.2
1.07 | Reset Caching Files | Apply Modfications | 0:10 | 600 | 0:35 | 130 | TRUE |  | 96 | TRUE |  | 184 | TRUE |  | 125 | TRUE |  | 117 | TRUE |  | 130.4 | 600 | 469.6
1.08 | Restart Services | Prepare Infrastructure | 0:10 | 600 | 0:45 | 411 | TRUE |  | 284 | TRUE |  | 402 | TRUE |  | 381 | TRUE |  | 312 | TRUE |  | 358 | 600 | 242
1.09 | Communicate Progress | Prepare Infrastructure | 0:05 | 300 | 0:55 | 68 | TRUE |  | 57 | TRUE |  | 94 | TRUE |  | 31 | TRUE |  | 65 | TRUE |  | 63 | 300 | 237
1.1 | Confirm Progress | Prepare Infrastructure | 0:05 | 300 | 1:00 | 311 | TRUE |  | 274 | TRUE |  | 300 | TRUE |  | 281 | TRUE |  | 282 | TRUE |  | 289.6 | 300 | 10.4
1.11 | Communicate Test Start | Testing | 0:05 | 300 | 1:05 | 43 | TRUE |  | 140 | TRUE |  | 64 | TRUE |  | 33 | TRUE |  | 67 | TRUE |  | 69.4 | 300 | 230.6
1.12 | Production Testing | Testing | 0:30 | 1800 | 1:10 | 1501 | TRUE |  | 1211 | TRUE |  | 1273 | TRUE |  | 1440 | TRUE |  | 1147 | TRUE |  | 1314.4 | 1800 | 485.6
1.13 | Communicate Test Results | Testing | 0:10 | 600 | 1:40 | 100 | TRUE |  | 196 | TRUE |  | 110 | TRUE |  | 241 | TRUE |  | 130 | TRUE |  | 155.4 | 600 | 444.6
1.14 | Sign off / completion |  | 0:05 | 300 | 1:50 | 88 | TRUE |  | 193 | TRUE |  | 109 | TRUE |  | 61 | TRUE |  | 33 | TRUE |  | 96.8 | 300 | 203.2
|  |  |  | 6900 |  | 3716 |  |  | 3495 |  |  | 3270 |  |  | 3594 |  |  | 3037 |  |  | 3422.4
No. ref | Task | Run 1 | Run 2 | Run 3 | Run 4 | Run 5 | Average Task Time | Expected | Average Lead Time
1.01 | Communicate Start | 83 | 104 | 38 | 74 | 33 | 66.4 | 300 | 233.6
1.02 | Copy Files | 249 | 218 | 256 | 192 | 253 | 233.6 | 300 | 66.4
1.03 | Back up Files | 177 | 189 | 104 | 177 | 206 | 170.6 | 300 | 129.4
1.04 | Shut Down Services | 203 | 181 | 79 | 145 | 176 | 156.8 | 600 | 443.2
1.05 | Backup of Database | 59 | 106 | 76 | 90 | 60 | 78.2 | 300 | 221.8
1.06 | Copy Files | 293 | 246 | 181 | 323 | 156 | 239.8 | 300 | 60.2
1.07 | Reset Caching Files | 130 | 96 | 184 | 125 | 117 | 130.4 | 600 | 469.6
1.08 | Restart Services | 411 | 284 | 402 | 381 | 312 | 358 | 600 | 242
1.09 | Communicate Progress | 68 | 57 | 94 | 31 | 65 | 63 | 300 | 237
1.1 | Confirm Progress | 311 | 274 | 300 | 281 | 282 | 289.6 | 300 | 10.4
1.11 | Communicate Test Start | 43 | 140 | 64 | 33 | 67 | 69.4 | 300 | 230.6
1.12 | Production Testing | 1501 | 1211 | 1273 | 1440 | 1147 | 1314.4 | 1800 | 485.6
1.13 | Communicate Test Results | 100 | 196 | 110 | 241 | 130 | 155.4 | 600 | 444.6
1.14 | Sign off / completion | 88 | 193 | 109 | 61 | 33 | 96.8 | 300 | 203.2
| Total | 3716 | 3495 | 3270 | 3594 | 3037 | 3422.4 | 6900 | 3477.6
| Category | Run 1 | Run 2 | Run 3 | Run 4 | Run 5 | Average | Expected | Lead
| Initialise Job | 83 | 104 | 38 | 74 | 33 | 66.4 | 300 | 233.6
| Copy Files | 249 | 218 | 256 | 192 | 253 | 233.6 | 300 | 66.4
| Prepare Infrastructure | 439 | 476 | 259 | 412 | 442 | 405.6 | 1200 | 794.4
| Apply Modfications | 423 | 342 | 365 | 448 | 273 | 370.2 | 900 | 529.8
| Prepare Infrastructure | 790 | 615 | 796 | 693 | 659 | 710.6 | 1200 | 489.4
| Testing | 1644 | 1547 | 1447 | 1714 | 1344 | 1539.2 | 2700 | 1160.8
| Total | 3628 | 3302 | 3161 | 3533 | 3004 | 3325.6 | 6600 | 3274.4